## GanttChart
Consulta+ | [7 empty] | Arrastar o quadrado abaixo para ver mais:
Cronograma do projeto
Início do projeto | 2025-09-15 |  |  | Mostrar Semana |  | 1 |  | Semana 1 | [6 empty] | Semana 2 | [6 empty] | Semana 3 | [6 empty] | Semana 4 | [6 empty] | Semana 5 | [6 empty] | Semana 6 | [6 empty] | Semana 7 | [6 empty] | Semana 8
[8 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03
 | time axis 2025-09-15 to 2025-11-09
Atividade | Atribuída a: | PREDECESSOR | Ínicio | Fim | Dias | % Conclusão | Dias de trabalho | time axis 2025-09-15 to 2025-11-09
Definição do tema do projeto | Todos |  | 2025-09-19 | 2025-09-20 | 5 | 100% | 1
Proposta do sistema | Todos |  | 2025-09-19 | 2025-09-20 | 5 | 100% | 1
Âmbito do sistema | Todos |  | 2025-09-19 | 2025-09-20 | 4 | 100% | 1
Regulamento Interno | Todos |  | 2025-09-19 | 2025-09-22 | 4 | 100% | 2
Template de Avaliação Interna | Todos |  | 2025-09-19 | 2025-09-20 | 2 | 100% | 1
Modelo das atas e convocatórias | Todos |  | 2025-09-19 | 2025-09-20 | 4 | 100% | 1
Critérios de Qualidade de Requisitos | Todos |  | 2025-09-19 | 2025-09-20 | 5 | 100% | 1
Cronograma | Todos |  | 2025-09-19 | 2025-09-26 | 3 | 100% | 6
Requisitos Funcionais e Não-Funcionais | Todos |  | 2025-09-27 | 2025-09-29 | 6 | 0% | 1
Casos de uso | Todos |  | 2025-09-27 | 2025-09-29 | 7 | 0% | 1
Backlog | Todos |  | 2025-09-27 | 2025-09-29 | 7 | 0% | 1
Diagramas de Sequência | Todos |  | 2025-09-29 | 2025-10-03 | 4 | 0% | 5
Diagrama de Estados | Todos |  | 2025-09-29 | 2025-10-03 | 5 | 0% | 5
Diagramas de Atividades | Todos |  | 2025-09-29 | 2025-10-03 | 3 | 0% | 5
Diagrama de Componentes | Todos |  | 2025-09-29 | 2025-10-03 | 4 | 0% | 5
Diagrama de Classes | Todos |  | 2025-09-29 | 2025-10-03 | 5 | 0% | 5
Diagrama ER | Todos |  | 2025-10-02 | 2025-10-10 | 3 | 0% | 7
Dicionário de dados | Todos |  | 2025-10-02 | 2025-10-10 | 6 | 0% | 7
Mockups | Todos |  | 2025-09-27 | 2025-10-10 | 5 | 0% | 10
Backend | Todos |  | 2025-10-11 | 2025-11-06 | 3 | 0% | 19
Testes Unitarios | Todos |  | 2025-10-11 | 2025-10-17 | 4 | 0% | 5
Testes Integração | Todos |  | 2025-10-18 | 2025-10-24 | 3 | 0% | 5
Requests Postman | Todos |  | 2025-10-25 | 2025-10-31 | 3 | 0% | 5
PipeLine funcional com testesno BE | Todos |  | 2025-11-01 | 2025-11-06 | 6 | 0% | 4
Frontend | Todos |  | 2025-11-07 | 2025-12-04 | 3 | 0% | 20
FrontEnd Web | Todos |  | 2025-11-07 | 2025-11-15 | 1 | 0% | 6
FrontEnd Mobile | Todos |  | 2025-11-16 | 2025-11-22 | 1 | 0% | 5
Testes Sistema | Todos |  | 2025-11-23 | 2025-11-28 | 1 | 0% | 5
PipeLine funcional com testes no FE | Todos |  | 2025-11-29 | 2025-12-02 | 1 | 0% | 2
FE Testes Aceitação | Todos |  | 2025-12-03 | 2025-12-04 | 1 | 0% | 2
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.